## Environment
OS | Browser
Windows10 | Chrome Version 102.0.5005.115 (Official Build) (64-bit)

## Web QA Assignment
|  |  |  | Passed | 18
|  |  |  | Failed | 11
|  |  |  | Block | 1
|  |  |  | N/A | 0
|  |  |  | Total | 30
Test By | Test Date | Build Test | TC # | Test Case Description | Test Steps | Expected Results | Actual Results | Test Status | Jira Ref | Automation test case | Comments
CRUD Articles
Create Articles
Preconditions: User login successfully User has permissions to create new articles User stays at home page
Lien Nguyen | 2022-06-18 | Version 001 | 1 | Create a new article with all required fileds | 1. From home, select New Article | 3. No error, the article published | Results as expected | Passed |  | CreateArticleAllValidFields
2. Input all fields:ex: article title, what's it about,content,…
3. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 2 | Create a new article missing all fileds | 1. From home, select New Article | User should see an error message :"Please input artitle title, article content,..." | No error message, article created successfully | Failed |  | CreateArticleMissingAllFields | Need to check with design document for sure
2. Leave all fields empty
3. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 3 | Create a new article missing article title | 1. From home, select New Article | User should see an error message :"Please input artitle title" | No error message, article created successfully | Failed |  | CreateArticleMissingArticleTitle | Need to check with design document for sure
2. Leave article title empty
3. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 4 | Create a new article missing article summary | 1. From home, select New Article | User should see an error message :"Please input artitle summary" | No error message, article created successfully | Failed |  | CreateArticleMissingArticleDes | Need to check with design document for sure
2. Leave article summary empty
3. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 5 | Be able to create a new article with no content | 1. From home, select New Article | No error message, article created successfully | As expected results | Passed |  | CreateArticleMissingArticleContent
2. Input content for article title, article summary
3. Leave article content empty
4. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 6 | Be able to input special characters when creating a new article | 1. From home, select New Article | No error message, article created successfully | As expected results | Passed |  | CreateArticleContainsSpecialCharacters
2. Input some special characters: ex: $%@ into article title box, summary box, content box
3. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 7 | Refresh page at "New Article" screen | 1. From home, select New Article | 2. Page is refreshed, home screen displayed | 2. error message displays "{"errors":{"message":"Not Found","error":{"status":404}}}" | Failed
2. Select Refresh icon to relead the current page
Lien Nguyen | 2022-06-18 | Version 001 | 8 | Back to previous screen from "New Article" screen | 1. From home, select New Article | 2. Home screen is displayed | As expected results | Passed
2. Select Back icon to go back to home
Update Articles
Preconditions: User created successfully at least one article User has permissions to update articles
Lien Nguyen | 2022-06-18 | Version 001 | 9 | Edit an article after creating | 1. From home, select New Article | 5. The article with the new title updated successfully | As expected results | Passed |  | UpdateArticlAfterCreating
2. Input all fields:ex: article title, what's it about,content,…
3. Press on "Publish Article"
4. Select Edit Article
5. Change article title to other value
6. Press on "Publish Article" to save the changes
Lien Nguyen | 2022-06-18 | Version 001 | 10 | Update an article from home > Your Feed | 1. At home > Your Feed > Select the created article to update | The article updated with new values | 1. No articles displayed at Your Feed | Failed
2. Press on "Edit Article"
3. Update article summary to a new value, article title to a new value
4. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 11 | Update an article from home > Global Feed | 1. At home > Global Feed > Select the created article to update | The article updated with new values | As expected results | Passed
2. Press on "Edit Article"
3. Update article summary to a new value, article title to a new value
4. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 12 | Update an article with missing all fields | 1. At home > Global Feed > Select the created article to update | Browser should display an error message, require user to input all required fields | No error message, article created successfully with all empty values | Failed
2. Press on "Edit Article"
3. Update all fields to empty values
4. Press on "Publish Article"
Lien Nguyen | 2022-06-18 | Version 001 | 13 | Update an article to previous values | 1. At home > Global Feed > Select the created article to update | The article updated with previous value, no errors | As expected results | Passed
2. Press on "Edit Article"
3. Update all fields to another values
4. Press on "Publish Article" to save the changes
5. Do above steps again to roll back to previous values
Lien Nguyen | 2022-06-18 | Version 001 | 14 | Update an article with special characters | 1. At home > Global Feed > Select the created article to update | The article updated successfully, no errors | As expected results | Passed
2. Press on "Edit Article"
3. Update all fields with normal and special characters
4. Press on "Publish Article" to save the changes
Read Articles
Preconditions: Has at least one new created articles
Lien Nguyen | 2022-06-18 | Version 001 | 15 | View the new created article from Your Feed | Go to home > Your Feed > check the created article | User can see the created article on Your Feed | The created article was not displayed on Your Feed, only see in Global Feed | Failed
Lien Nguyen | 2022-06-18 | Version 001 | 16 | View the new created article from Global Feed | 2. Go to home > Global Feed | User can see the created article on Global Feed | As expected results | Passed
Preconditions: User stays at home page Has at least one updated articles: updated article title, content
Lien Nguyen | 2022-06-18 | Version 001 | 17 | View updated article from Your Feed | Go to "Your Feed" > check the updated article | User can see the created article with new title from Your Feed | No articles listed in Your Feed, only see from Global Feed | Failed
Lien Nguyen | 2022-06-18 | Version 001 | 18 | View updated article from Global Feed | Go to "Global Feed" > check the updated article | User can see the created article with new title from Global Feed | As expected results | Passed
Has at least one article created by other users
Lien Nguyen | 2022-06-18 | Version 001 | 19 | Read article of other users | 1. From Home > Global Feed > Select one available article (created by another one) | 1. Can select the article, no issue 2. Be able to read article title, summary, content, no options to delete, edit | As expected results | Passed
2. Check the selected article
Lien Nguyen | 2022-06-18 | Version 001 | 20 | Read articles from the list at Global Feed | 1. From Home > Global Feed | Be able to see the list of articles from Gobal Feed, each article will displays User, Created Datetime, Article title, Article summary(description). (Article title will be bold) | As expected results | Passed
2. Scroll down/up to see list of articles
Delete Articles
Has at least one article created by other users and one created by current user
Lien Nguyen | 2022-06-18 | Version 001 | 21 | Delete your own articles after creating | 1. Frome home > New Article | 4. The article deleted successfully 5. Not see the article from Global Feed/Your Feed | As expected results | Passed |  | DeleteArticleAfterCreating | Have known issues with Your Feed
2. Input all required fields
3. Press on "Publish Article" to create a new one
4. Press on "Delete Article" on the top of screen to delete
5. Verify results at Global Feed/Your Feed
Lien Nguyen | 2022-06-18 | Version 001 | 22 | Delete your own article after updating | 1. From home > select your created article | 3. The article updated successfully 4. The article deleted successfully 5. Not see the article from Global Feed/Your Feed | As expected results | Passed |  |  | Have known issues with Your Feed
2. Input new values to update
3. Press on "Publish Article" to update
4. Press on "Delete Article" on the top of screen to delete
5. Verify results at Global Feed/Your Feed
Lien Nguyen | 2022-06-18 | Version 001 | 23 | Delete your own articles from Global Feed | 1. From Home > Global Feed > select your created article | The article deleted, not see anymore from Global Feed | As expected results | Passed
2. Press on "Delete Article" to delete
3. Verify results from Global Feed
Lien Nguyen | 2022-06-18 | Version 001 | 24 | Delete your own articles from Your Feed | 1. From Home > Your Feed > select your created article | The article deleted, not see anymore from Your Feed | 1. At this step, not see any articles | Failed
2. Press on "Delete Article" to delete
3. Verify results from Your Feed
Lien Nguyen | 2022-06-18 | Version 001 | 25 | Delete the article created by another user | 1. From Home > Global Feed > Select one available article (created by another user) | Not see Edit and Delete buttons as it's created by another user | As expected results | Passed
Favorite articles
Preconditions: User has enough permissions to add favorite articles Login successfully Has some articles on Global Feed
Lien Nguyen | 2022-06-18 | Version 001 | 26 | Verify Favorite default icon from Global Feed | Go to Home > Global Feed | One article will have one favorite button beside | As expected results | Passed |  |  |  | Need to confirm with design document for sure
[5 empty] | Not select any favorite articles then go to your profile > Favorited Posts | No articles displayed, should have message "No articles are here... yet." | As expected results
Lien Nguyen | 2022-06-18 | Version 001 | 27 | Add favorite article from Global Feed | Go to Home > Global Feed > Click on favorite button beside the article you want to add favorite | Favorite button text will be changed from 0 to 1 | As expected results | Failed
[5 empty] | Refresh the page | The favorite button still keep the new value | The favorite button reset value to 0
[5 empty] | Go to your profile > Favorited Posts | The added favorite article will be listed here | Browser displays "No articles are here... yet."
Lien Nguyen | 2022-06-18 | Version 001 | 28 | Add multiple favorite articles from Global Feed | Go to Home > Global Feed > Click on multiple favorite buttons beside the articles you want to add favorite (from other people and your articles) | Favorite button text will be changed from 0 to 1 for each selected article | As expected results | Failed
[5 empty] | Go to your profile > Favorited Posts | All added favorite articles will be listed here | Browser displays "No articles are here... yet."
Lien Nguyen | 2022-06-18 | Version 001 | 29 | Remove favorite articles from Global Feed | Go to Home > Global Feed | Selected favorite articles displayed here with correct favorite buttons | As expected results | Passed
[5 empty] | Add some favorite articles | Favorite button text changed from 0 to 1 | As expected results
[5 empty] | Click on current selected favorite article buttons to remove from favorite list | Favorite button text changed from 1 to 0 | As expected results
Lien Nguyen | 2022-06-18 | Version 001 | 30 | Remove favorite articles from profile > Favorited Posts | To Be Updated (currently, having bugs on this page) |  |  | Blocked